## Sheet1
Team 17: 5 Blind Mice Project Timeline (Spring 2020)
Task | Week
| Jan 13-19 | Jan 20-26 | Jan 27-Feb2 | Feb 3-9 | Feb 10-16 | Feb 17-23 | Feb 24-Mar 31 | Mar 2-8 | Mar 9-15 | Mar 16-22 | Mar 23-29 | Mar 30-Apr 5 | Apr 6-12 | Apr 13-19 | Apr 20-26 | Apr 27-May 3
Project Proposal
Design document rev 1
Solution proposal
Braille reader background research, finalize subsystem design specs, individual subsystem design
Revision for Design Document
Design document rev 2
ADC algorithm research (tutorial)
Audio mapping algorithm research
Update on subsystem diagram for audio mapping part
Install aeneas libraries, audio and ebook files for testing for audio mapping
Build and test Audio Mapping on Python using aeneas library
Install System Workbench
Manager meeting
Use feedback from MM to revise subsystem design
Testing mapping file accuracy
Audio parsing based on mapping file
Configuration of ADC (potentiometer, power)
Testing ADC output (single/continuous)
Configure prescaler factor and test on LED
Change speed dial to button and using on board push button to change lighting frequency of LED
Prepare for midterm demo (update on subsystem design document, run complete test on all subsystem parts)
Skills assessment (preliminary)
Midterm demo
Design document rev 3
Integration of subsystems on microcontroller
Update subsystem schematic for PCB design
PCB design for the team (order, integration, soldering)
Audio speed adjustment
PCB review
Skills assessment (deadline)
PCB exception requests due
Test sample production (4 speed) and pulse configuration research
Audio syncing test and latency calculation
Prepare for midterm demo(finalize design document, prepare presentation slides)
Final demo
Final design review
Design document - final
ABET
*Bolds are major deadlines
*Unbolds are specific tasks